## Project Status
Project | Function | Function List | Status | Owner | Plan | Due_Date | Remark
PreNPI (Phase1)
| DataBase規劃與建構 | DataBase規劃與建構
|  | npiPOR Table | Finish | TW | 1/11 | 2/E
|  | npiAPP Table | Finish | TW | 1/15 | 2/E
|  | npiManual Table | Finish | TW | 1/28 | 2/E
|  | npiCAP Table |  | TW
|  | npiEA Table | Finish | TW |  | 2/E
|  | npiRelation Table |  | TW
|  | npiImportData Table | Finish | TW | 1/18 | 2/E
|  | npiManual Table | Finish | TW | 1/25 | 2/E
|  | npiHistory Table | Finish | TW |  | 3/M
| POR Form Web UI | Add_npiPOR | Finish | TW |  | 2/E
|  | Update_npiPOR | Finish | TW |  | 2/E
|  | Query_npiPOR | Finish | TW |  | 2/E
|  | Export Excel |  | TW
| Application Form Web UI | Add_npiAPP | Finish | TW |  | 2/E
|  | Update_npiAPP | Finish | TW |  | 2/E
|  | Query_npiAPP | Finish | TW |  | 2/E
|  | Export Excel |  | TW
| Manual Web UI | Add_npiMan | Finish | TW |  | 2/E
|  | Update_npiMan | Finish | TW |  | 2/E
|  | Query_npiMan | Finish | TW |  | 2/E
| DIF/Q&R/DRC Excel Import Function | Add_xlsImport | Finish | TW |  | 2/E
|  | Update_xlsImport | Finish | TW |  | 2/E
|  | Query_xlsImport | Finish | TW |  | 2/E
| EA TRA Web UI | View_npiEATra | Finish | Bruno |  | 3/E | 比對邏輯
|  | Save_npiEATra | OnGoing | Bruno |  | 4/B | 版本管控
|  | Query_npiEATra | OnGoing | Bruno |  | 4/B
|  | Search_npiPOR | Finish | Bruno |  | 3/E
|  | Export Excel | OnGoing | Bruno
| History紀錄 | Query_npiHis | OnGoing | TW |  | 4/E
| New POR轉POR Golden Table | 新增/修改/刪除修改介面

## IssueList
Date | Excel Type | Isseu | Result | Owner | Finsh | Action
1/4 | EP_TRA | Die size(mm*mm):DIF! D5 x DIF! G5 | OK | JJ | 1/5 | 改成DIF! D19 x DIF! G19
1/4 | APP Form | Application form! F12/Application form! F13 =>正規劃格式 | OK | JJ | 1/5 | 提供一版正規化後格式
1/4 | EP_TRA | 1.ByManual=> 是否加在Application form介面內 | OK | JJ | 1/7 | 會議確認,將by manual的部分將整理於Manual Form, User須將此資料輸入此資料後,EP_TRA比對才有意義
1/4 | EP_TRA | Plating Solder與 Pating Solder POR資料確認 :無法從Pating Solder POR得到的資料 | OK | JJ | 1/7
1/4 | EP_TRA | 確認Plating Solder中Capability 的資料來源 | OK | JJ | 1/7 | 建立新增進版功能
1/6 | APP Form | 可否提供哪些製程,其CD Design有哪些相對應選項?? | OK | JJ | 1/19 | JJ提供分辨PKG Type Rule
1/7 | DRC | DRC內容確認 | OK | JJ | 1/7 | 1.Import Excel DRC方式,擷取需要使用的欄位資料給予EP_TRA比對 2.暫不開發DRC輸入介面
1/15 | POR | PI edgeinside seal ring字元長度?? Wafer PSV Type Thickness項目重複 | OK | JJ | 1/15
1/15 | EP_TRA | 有些資料欄位是沒有POR與CAP的可以參考??
1/15 | Manual | 請提供By Manual 的資料格式?? | OK | JJ | 1/19
1/15 | Capability | 請確認Capability格式??

## DataTable
npiSource |  |  |  |  | npiAPP |  |  |  |  | npiPOR |  |  |  | npiManual |  |  |  | npiImportData |  |  |  | npiEACap |  |  |  | npiEATra
資料行名稱 | PK | 資料型態 | 允許Null |  | 資料行名稱 | PK | 資料型態 | 允許Null |  | 資料行名稱 | PK | 資料型態 | 允許Null | 資料行名稱 | PK | 資料型態 | 允許Null | 資料行名稱 | PK | 資料型態 | 允許Null | 資料行名稱 | PK | 資料型態 | 允許Null | 資料行名稱 | PK | 資料型態 | 允許Null
SID | V | int |  |  | New_Customer | V | varchar(30) |  |  | Por_Customer | V | varchar(30) |  | New_Customer | V | varchar(30) |  | New_Customer | V | varchar(30)
Stype |  | varchar(5) |  |  | New_Device | V | varchar(30) |  |  | Por_Device | V | varchar(30) |  | New_Device | V | varchar(30) |  | New_Device | V | varchar(30)
[5 empty] | SType | V | varchar(5) |  |  | SType | V | varchar(5) |  | Stype | V | varchar(5) |  | Stype |  | varchar(5)
[5 empty] | UpdateTime |  | Datatime |  |  | UpdateTime |  | Datatime |  | UpdateTime |  | Datatime |  | UpdateTime |  | Datatime
npiMAP |  |  |  |  | npiUser |  | varchar(10) | V |  | npiUser |  | varchar(10) | V | npiUser |  | varchar(10) | V | npiUser |  | varchar(10) | V | Cap_01
資料行名稱 | PK | 資料型態 | 允許Null |  | APP_Status |  | varchar(1) | V |  | Por_Status |  | varchar(1) | V | Man_Status |  | varchar(1) | V | Im_Name |  | varchar(30) | V | Cap_02
MID | V | int |  |  | APP_PKG |  | varchar(20) | V |  | Por_01 | V | varchar(5) |  | Man_01 |  | varchar(20) | V | Im_Pos | V | varchar(5) |  | Cap_03
Mtype |  | varchar(5) |  |  | APP_01 |  | varchar(50) | V |  | Por_02 |  | varchar(25) | V | Man_02 |  | varchar(10) | V | Im_Value |  | varchar(30) | V | Cap_04
Mname |  | varchar(30) |  |  | APP_02 |  | varchar(5) | V |  | Por_03 |  | varchar(5) | V | Man_03 |  | varchar(5) | V |  |  |  |  | Cap_05
Mpos |  | varchar(5) |  |  | APP_03 |  | varchar(5) | V |  | Por_04 |  | varchar(10) | V | Man_04 |  | varchar(50) | V |  |  |  |  | Cap_06
[5 empty] | APP_04 |  | varchar(30) | V |  | Por_05 |  | varchar(10) | V | Man_05 |  | varchar(5) | V |  |  |  |  | Cap_07
npiEAMap |  |  |  |  | APP_05 |  | varchar(30) | V |  | Por_06 |  | varchar(5) | V | Man_06 |  | varchar(10) | V |  |  |  |  | Cap_08
資料行名稱 | PK | 資料型態 | 允許Null |  | APP_06 |  | varchar(15) | V |  | Por_07 |  | varchar(10) | V | Man_07 |  | varchar(10) | V |  |  |  |  | Cap_09
EAID | V | int |  | 1~65 | APP_07 |  | varchar(15) | V |  | Por_08 |  | varchar(1) | V | Man_08 |  | varchar(10) | V |  |  |  |  | Cap_10
Stype |  | varchar(5) | V |  | APP_08 |  | varchar(20) | V |  | Por_09 |  | varchar(20) | V | Man_09 |  | varchar(5) | V | npiHistory |  |  |  | Cap_11
Spos |  | varchar(15) | V |  | APP_09 |  | varchar(5) | V |  | Por_10 |  | varchar(10) | V | Man_10 |  | varchar(5) | V | 資料行名稱 | PK | 資料型態 | 允許Null | Cap_12
EAType |  | varchar(20) | V |  | APP_10 |  | varchar(5) | V |  | Por_11 |  | varchar(1) | V | Man_11 |  | varchar(10) | V | His_Time | V | Datatime |  | Cap_13
EAName |  | varchar(50) | V |  | APP_11 |  | varchar(5) | V |  | Por_12 |  | varchar(15) | V | Man_12 |  | varchar(5) | V | npiUser |  | varchar(10) | V | Cap_14
[5 empty] | APP_12 |  | varchar(5) | V |  | Por_13 |  | varchar(5) | V | Man_13 |  | varchar(10) | V | npiFun |  | varchar(15) | V | Cap_15
[5 empty] | APP_13 |  | varchar(25) | V |  | Por_14 |  | varchar(20) | V | Man_14 |  | varchar(20) | V | His_SQL |  | varchar(Max) | V | Cap_16
[5 empty] | APP_14 |  | varchar(5) | V |  | Por_15 |  | varchar(40) | V | Man_15 |  | varchar(10) | V |  |  |  |  | Cap_17
[5 empty] | APP_15 |  | varchar(5) | V |  | Por_16 |  | varchar(30) | V | Man_16 |  | varchar(20) | V |  |  |  |  | Cap_18
[5 empty] | APP_16 |  | varchar(25) | V |  | Por_17 |  | varchar(30) | V | Man_17 |  | varchar(10) | V |  |  |  |  | Cap_19
[5 empty] | APP_17 |  | varchar(5) | V |  | Por_18 |  | varchar(15) | V | Man_18 |  | varchar(10) | V | npiFun |  |  |  | Cap_20
[5 empty] | APP_18 |  | varchar(5) | V |  | Por_19 |  | varchar(10) | V | Man_19 |  | varchar(10) | V | npiPOR_ | add/edit/del |  |  | Cap_21
[5 empty] | APP_19 |  | varchar(5) | V |  | Por_20 |  | varchar(5) | V | Man_20 |  | varchar(5) | V | npiAPP | add/edit/del |  |  | Cap_22
[5 empty] | APP_20 |  | varchar(5) | V |  | Por_21 |  | varchar(15) | V | Man_21 |  | varchar(5) | V | npiMan | add/edit/del |  |  | Cap_23
[5 empty] | APP_21 |  | varchar(5) | V |  | Por_22 |  | varchar(10) | V | Man_22 |  | varchar(5) | V | npiImp | add/del |  |  | Cap_24
[5 empty] | APP_22 |  | varchar(5) | V |  | Por_23 |  | varchar(1) | V |  |  |  |  | npiEPTRA_ | cmp/save/del |  |  | Cap_25
[5 empty] | APP_23 |  | varchar(15) | V |  | Por_24 |  | varchar(1) | V | [8 empty] | Cap_26
[5 empty] | APP_24 |  | varchar(15) | V |  | Por_25 |  | varchar(1) | V | [8 empty] | Cap_27
[5 empty] | APP_25 |  | varchar(25) | V |  | Por_26 |  | varchar(10) | V | [8 empty] | Cap_28
[5 empty] | APP_26 |  | varchar(5) | V |  | Por_27 |  | varchar(25) | V | [8 empty] | Cap_29
[5 empty] | APP_27 |  | varchar(5) | V |  | Por_28 |  | varchar(15) | V | [8 empty] | Cap_30
[5 empty] | APP_28 |  | varchar(25) | V |  | Por_29 |  | varchar(5) | V | [8 empty] | Cap_31
[5 empty] | APP_29 |  | varchar(5) | V |  | Por_30 |  | varchar(15) | V | [8 empty] | Cap_32
[5 empty] | APP_30 |  | varchar(5) | V |  | Por_31 |  | varchar(25) | V | [8 empty] | Cap_33
[5 empty] | APP_31 |  | varchar(5) | V |  | Por_32 |  | varchar(25) | V | [8 empty] | Cap_34
[5 empty] | APP_32 |  | varchar(5) | V |  | Por_33 |  | varchar(20) | V | [8 empty] | Cap_35
[5 empty] | APP_33 |  | varchar(5) | V |  | Por_34 |  | varchar(10) | V | [8 empty] | Cap_36
[5 empty] | APP_34 |  | varchar(5) | V |  | Por_35 |  | varchar(5) | V | [8 empty] | Cap_37
[5 empty] | APP_35 |  | varchar(15) | V |  | Por_36 |  | varchar(5) | V | [8 empty] | Cap_38
[5 empty] | APP_36 |  | varchar(15) | V |  | Por_37 |  | varchar(10) | V | [8 empty] | Cap_39
[5 empty] | APP_37 |  | varchar(25) | V | varchar(1) | Por_38 |  | varchar(15) | V | [8 empty] | Cap_40
[5 empty] | APP_38 |  | varchar(5) | V | varchar(25) | Por_39 |  | varchar(15) | V | [8 empty] | Cap_41
[5 empty] | APP_39 |  | varchar(5) | V | varchar(1) | Por_40 |  | varchar(15) | V | [8 empty] | Cap_42
[5 empty] | APP_40 |  | varchar(25) | V | varchar(25) | Por_41 |  | varchar(15) | V | [8 empty] | Cap_43
[5 empty] | APP_41 |  | varchar(5) | V | varchar(25) | Por_42 |  | varchar(100) | V | [8 empty] | Cap_44
[5 empty] | APP_42 |  | varchar(5) | V | varchar(25) | Por_43 |  | varchar(5) | V | [8 empty] | Cap_45
[5 empty] | APP_43 |  | varchar(5) | V | varchar(10) | Por_44 |  | varchar(10) | V | [8 empty] | Cap_46
[5 empty] | APP_44 |  | varchar(5) | V | varchar(25) | Por_45 |  | varchar(5) | V | [8 empty] | Cap_47
[5 empty] | APP_45 |  | varchar(5) | V |  | Por_46 |  | varchar(20) | V | [8 empty] | Cap_48
[5 empty] | APP_46 |  | varchar(5) | V |  | Por_47 |  | varchar(10) | V | [8 empty] | Cap_49
[5 empty] | APP_47 |  | varchar(15) | V |  | Por_48 |  | varchar(10) | V | [8 empty] | Cap_50
[5 empty] | APP_48 |  | varchar(15) | V |  | Por_49 |  | varchar(10) | V | [8 empty] | Cap_51
[5 empty] | APP_49 |  | varchar(25) | V |  | Por_50 |  | varchar(10) | V | [8 empty] | Cap_52
[5 empty] | APP_50 |  | varchar(5) | V |  | Por_51 |  | varchar(10) | V
[5 empty] | APP_51 |  | varchar(5) | V |  | Por_52 |  | varchar(10) | V
[5 empty] | APP_52 |  | varchar(25) | V |  | Por_53 |  | varchar(10) | V
[5 empty] | APP_53 |  | varchar(5) | V |  | Por_54 |  | varchar(10) | V
[5 empty] | APP_54 |  | varchar(5) | V |  | Por_55 |  | varchar(5) | V
[5 empty] | APP_55 |  | varchar(5) | V
[5 empty] | APP_56 |  | varchar(5) | V
[5 empty] | APP_57 |  | varchar(5) | V
[5 empty] | APP_58 |  | varchar(5) | V
[5 empty] | APP_59 |  | varchar(15) | V
[5 empty] | APP_60 |  | varchar(15) | V
[5 empty] | APP_61 |  | varchar(25) | V
[5 empty] | APP_62 |  | varchar(5) | V
[5 empty] | APP_63 |  | varchar(5) | V
[5 empty] | APP_64 |  | varchar(25) | V
[5 empty] | APP_65 |  | varchar(5) | V
[5 empty] | APP_66 |  | varchar(5) | V
[5 empty] | APP_67 |  | varchar(5) | V
[5 empty] | APP_68 |  | varchar(5) | V
[5 empty] | APP_69 |  | varchar(5) | V
[5 empty] | APP_70 |  | varchar(5) | V
[5 empty] | APP_71 |  | varchar(15) | V
[5 empty] | APP_72 |  | varchar(15) | V
[5 empty] | APP_73 |  | varchar(25) | V
[5 empty] | APP_74 |  | varchar(5) | V
[5 empty] | APP_75 |  | varchar(5) | V
[5 empty] | APP_76 |  | varchar(25) | V
[5 empty] | APP_77 |  | varchar(5) | V
[5 empty] | APP_78 |  | varchar(5) | V
[5 empty] | APP_79 |  | varchar(5) | V
[5 empty] | APP_80 |  | varchar(5) | V
[5 empty] | APP_81 |  | varchar(5) | V
[5 empty] | APP_82 |  | varchar(5) | V
[5 empty] | APP_83 |  | varchar(15) | V
[5 empty] | APP_84 |  | varchar(15) | V
[5 empty] | APP_85 |  | varchar(1) | V
[5 empty] | APP_86 |  | varchar(25) | V
[5 empty] | APP_87 |  | varchar(1) | V
[5 empty] | APP_88 |  | varchar(25) | V
[5 empty] | APP_89 |  | varchar(25) | V
[5 empty] | APP_90 |  | varchar(25) | V
[5 empty] | APP_91 |  | varchar(10) | V
[5 empty] | APP_92 |  | varchar(25) | V

## Application Form欄位定義
| Customer | AMD
| New Device | KINGSTON |  |  | Add New Application Form
| New Mask圖面設計繪製 (A) |  |  | APP01
| 設計修改 (A+B) |  |  | APP02 |  |  |  | Customer : |  | AMD-CPU | APP04
| Study Case (A+C) |  |  | APP03 |  |  |  | Device : |  | KINGSTON | APP05
APP06 | 申請日期 (REQUEST DATE) |  | 2015-04-27 |  |  |  | 希望完成日期 (SCHEDULE COMPLETION DATE) | [5 empty] | APP07
【A】設計條件/需求(Design Request)
| PKG type: | [8 empty] | APP08
| Bump Height: |  |  |  | BH | APP09 | +/- | APP10 | %
| Bump Diameter PI anchor hole: |  |  |  | BD | APP11 | +/- | APP12 | %
|  |  |  | Material | THK-Value | THK | THK-Toler | Exp. Tool | Mask size | Field # per reticle | CD-Value | Design CD | CD-Toler | Size-Value | Feature Size | Size-Toler | Shape | Process type
|  |  |  | APP13 | APP14 |  | APP15 | APP16 | APP17 | APP18 | APP19 |  | APP20 | APP21 |  | APP22 | APP23 | APP24
| CD Design: |  |  | PI@Bump | 5 | +- | 1um | AP200/AP300 | 6" | 2 | 45 | +- | 1um | 45 | +- | 6um | Circle | Plating
|  |  |  | Plating@UBM | 3.9 | +- | 1.04um | MA300 | 14" |  | 75 | +- | 1um | 80 | +- | 4um | Circle | Plating
|  |  |  | APP25 | APP26 |  | APP27 | APP28 | APP29 | APP30 | APP31 |  | APP32 | APP33 |  | APP34 | APP35 | APP36
|  |  |  | APP37 | APP38 |  | APP39 | APP40 | APP41 | APP42 | APP43 |  | APP44 | APP45 |  | APP46 | APP47 | APP48
|  |  |  | APP49 | APP50 |  | APP51 | APP52 | APP53 | APP54 | APP55 |  | APP56 | APP57 |  | APP58 | APP59 | APP60
|  |  |  | APP61 | APP62 |  | APP63 | APP64 | APP65 | APP66 | APP67 |  | APP68 | APP69 |  | APP70 | APP71 | APP72
|  |  |  | APP73 | APP74 |  | APP75 | APP76 | APP77 | APP78 | APP79 |  | APP80 | APP81 |  | APP82 | APP83 | APP84
| Dummy Bump request (for plating +Aligner mask): |  |  | APP37 | 不需要dummy bumps |  |  | 需要dummy bumps |  | check Box
【B】修改參考(Design Reference)
| 1. Reference Mask drawing #: | [8 empty] | APP38
| 2. New Drawing No? |  |  |  | Yes No |  |  |  |  | APP39 | check Box
| 3. Change item | [8 empty] | APP40
【C】開發研究 (Study)
| 1. New structure | [8 empty] | APP41
| 2. New Bias | [8 empty] | APP42
| 3. Photoresist |  |  |  |  | P-photo |  | N-photo |  | APP43 | 下拉選單
| 4. Other | [8 empty] | APP44
*Application Form Function:
1.新增/刪除/修改/查詢功能
2.Export Excel File
*Mask Design Application Form:
1) EP REPSV-12(8)-LF(EU): 2 layers, PI@Bump and Plating@UBM.
2)As to other PKG type, I let owner to update when we fan out to
other PKG type.

## POR欄位定義
1.新增/刪除/修改/查詢功能
2.Export Excel File
*此顏色為查詢條件
| POR_01 | POR_02 | POR_03 | POR_04 | POR_05 | POR_06 | POR_07 | POR_08 | POR_09 | POR_10 | POR_11 | POR_12 | POR_13 | POR_14 | POR_15 | POR_16 | POR_17 | POR_18 | POR_19 | POR_20 | POR_21 | POR_22 | POR_23 | POR_24 | POR_25 | POR_26 | POR_27 | POR_28 | POR_29 | POR_30 | POR_31 | POR_32 | POR_33 | POR_34 | POR_35 | POR_36 | POR_37 | POR_38 | POR_39 | POR_40 | POR_41 | POR_42 | POR_43 | POR_44 | POR_45 | POR_46 | POR_47 | POR_48 | POR_49 | POR_50 | POR_51 | POR_52 | POR_53 | POR_54 | POR_55
| 5 | 50 | 5 | 10 | 10 | 5 | 10 | 1 | 20 | 10 | 1 | 15 | 5 | 20 | 40 | 30 | 30 | 15 | 10 | 5 | 15 | 10 | 1 | 1 | 1 | 10 | 25 | 15 | 5 | 15 | 25 | 25 | 20 | 10 | 5 | 5 | 10 | 15 | 15 | 15 | 15 | 100 | 5 | 10 | 5 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5
Select Item | POR_01: 1; POR_02: 2; POR_03: 3; POR_04: 4; POR_05: 5; *此顏色為查詢條件 POR_11: 6; *此顏色為查詢條件 POR_14: 7; *此顏色為查詢條件 POR_17: 8
Device | 1. Production Site | 2.PKG | 3.Wafer Tech.(nm) | 4.FAB | 5.Wafer PSV type / Thickness | 6.PR Type | 7.Ti etching Chemical(T89/DHF) | 8.Tin Shell Bake (Y/N) | 9.PI rougness (SPIL STD:BGM3A) | 10.Bump resistance capability (SPIL STD:<30mhom) | 11.推大球100% RVSI(Y/N) | 12.LowK | 13.PR thickness | 14.Customer | PROD | *UBM type / Thickness | Device | Die size(mm) | Min. Bump pitch | Final Metal Pad type | Wafer PSV type / Thickness | Bump Density | RV hole on Al pad | Probing on pad(Y/N) | Seal-Ring Protected by SiN (Y/N) | Passivation type / Thickness | UBM Overlap PSV (≧8um) | UBM insdie final metal for FOC (um) | UBM Size | REPSV PI Opening Size | PI via opening bottom edge to pad psv. Edge (um) | PI edge inside seal ring (um) | Bump type | UBM Plating Area | Bump Height(um) | UBM/SMO ratio | BH/UBM ratio | Process / Machine | Material | Measurement tool | Reliability | Remark | Mushroon space | Mushroon CD | Bump diameter | C/P probe card type( Vertical probe/ Membrane) | Min final metal pad to seal ring (um) | Bump to bump space | SMO | UBM density | Die size X(mm) | Die size Y(mm) | Bump count | Corner UBM density | Passivation type / Thickness
GK106 | CS | EP REPSV-12-EU | 28 | TSMC | SiN | AZ | T89 | N | BGM3A:15~30nm | <20 mohm | N | ELK | 50 | NV | 12-BP-PSV-EP-EU-PI-TCN-9D-14 | Ti1K/Cu5K/Ni3um | GK106 | 16*13 | 180 | Al | SiN/1.1um | 19.1 | N | N | Y | HD4104 | 22.5 | NA | 90 | 35 | 17.5 | 5 | Plated 63Sn/37Pb | 0.82 | 90 | 0.94 | 1 | NA | NA | NA | NA |  | 29 | 151 | 112 | Vertical probe | 6.7 | 68 | 95 | 12.84% | 16 | 13 | 4198 |  | 5um

## Manual欄位定義
New Customer |  | AMD-CPU | New_Customer | varchar | 30
New Device |  | KINGSTON | New_Device | varchar | 30
Wafer PSV type / Thickness |  | SiN | Man_01 | varchar | 20
PI type |  | HD4104 | Man_02 | varchar | 10
PI Thickness (um) |  | 5um | Man_03 | varchar | 5
UBM type / Thickness (um) |  | Ti1K/Cu3K/Ni3.5um | Man_04 | varchar | 50
PR thickness(um) |  | 50 | Man_05 | varchar | 5
UBM insdie final metal for FOC (um) |  | NA | Man_06 | varchar | 10
UBM Plating Area(dm2) |  | 1.336 | Man_07 | varchar | 10
UBM Density (UBM Area/Die Area) |  | 20.08% | Man_08 | varchar | 10
Mushroom CD(um) |  | 106 | Man_09 | varchar | 5
Min Mushroom space(um) |  | 44 | Man_10 | varchar | 5
Bump Density (Bump Q'ty/Die Area) |  | 39.95 | Man_11 | varchar | 10
BH/UBM ratio |  | 1 | Man_12 | varchar | 5
Bump Coplanarity |  | <20 um | Man_13 | varchar | 10
Bump Shear Strenght |  | LF: >2.5 g/mil^2 | Man_14 | varchar | 20
Bump void |  | <10 % | Man_15 | varchar | 10
PI Rougness (Ra) |  | BGM3A:15~30nm | Man_16 | varchar | 20
August | Gross die () | 294 | Man_17 | varchar | 10
| Expose pad | NA | Man_18 | varchar | 10
RVSI | Gross die | 294 | Man_19 | varchar | 10
Bump to bump space (um) |  | 60 | Man_20 | varchar | 5
SMO (um) |  | 80 | Man_21 | varchar | 5
UBM/SMO ratio |  | 1 | Man_22 | varchar | 5

## Cap_Relation 欄位定義
Key item |  |  |  | Capability | npiCap |  |  | Effect stage | npiEff | Potential Effect | npiPot
PROD |  |  |  | - | Cap_01 |  |  | -- | Eff_01 | -- | Pot_01
Device Information | 1 | Customer |  | - | Cap_02 |  |  | -- | Eff_02 | -- | Pot_02
| 2 | Device |  | - | Cap_03 |  |  | -- | Eff_03 | -- | Pot_03
| 3 | Die size(mm*mm) |  | 4*4~23*23 | Cap_04 | E5 | H5 | Assembly Reliability | Eff_04 | Bump crack RT fail | Pot_04
| 4 | C/P probe card type |  | Vertical probe Membrane | Cap_05 | E6 | H6 | CP | Eff_05 | Probe card damage | Pot_05
| 5 | Probing on bump pad (Y/N) |  | Not Allowed | Cap_06 | E7 | H7 | UBM PHOTO PLAT | Eff_06 | UBM poor coverage Pad damage Pad damage | Pot_06
Wafer Information | 6 | Wafer Fab |  | TSMC,UMC,GF,SMIC | Cap_07 | E8 | H8 | Assembly Reliability | Eff_07 | Low K crack RT fail | Pot_07
| 7 | Wafer tech.(nm) |  | 28~130 | Cap_08 | E48 | H48 | Assembly Reliability | Eff_08 | Low K crack RT fail | Pot_08
| 8 | Low K Type |  | ELK | Cap_09 | E9 | H9 | Assembly Reliability | Eff_09 | Low K crack RT fail | Pot_09
| 9 | Final Metal Pad type |  | Al Cu | Cap_10 | E10 | H10 | UBM Assembly | Eff_10 | BS/BP fail RT fail | Pot_10
| 10 | RV hole(Y/N) |  | Not Allowed | Cap_11 | E11 | H11 | PHOTO PLAT | Eff_11 | Pad damage | Pot_11
| 11 | Wafer PSV type / Thickness |  | SiN | Cap_12 | E12 | H12 | PI1 UBM PHOTO PLAT ETCH Reliability | Eff_12 | 1.PI profile non-smooth 2.Metal film dis-continuity UBM poor coverage Pad damage Pad damage PSV roughness RT fail | Pot_12
| 12 | Seal-Ring Protected by SiN (Y/N) |  | Y | Cap_13 | E13 | H13 | PI1 UBM PLAT ETCH | Eff_13 | PI delam Poor step coverage 1. Metal peeling 2. BH/BC OOS Metal peeling | Pot_13
Bump structure | 13 | PKG Type |  | EP REPSV-12-EU EP REPSV-12-LF EP FOC-12-EU EP FOC-12-LF EP REPSV-8-LF | Cap_14 |  |  | -- | Eff_14 | -- | Pot_14
| 14 | PI type |  | HD4104 | Cap_15 | E15 | H15 | PI1 UBM ETCH DESCUM Assembly | Eff_15 | 1.PI CD OOS 2.PI residue 3. RS OOS 4. PI THK abnormal 5. PI Crack 6. Abnormal PI profile 1. BR OOS 2. UBM dis-connnection/poor step coverage 3. UBM peeling 1.PI roughness OOS 2.Metal residue 3. Undercut OOS 4.BL OOS 5. Irregular bump/Bump wrinkle 6. Solder burst 1. BR OOS 2. Metal residue 3. PI damage 4. PI roughness OOC 5. PI delamination 6. BL OOS 1.Glue residual 2.Bump crack 3.UBM crack 4.Md/UF delam | Pot_15
| 15 | PI Thickness (um) |  | 5um | Cap_16 | E49 | H49 | PI1 UBM PPHO PLAT DESCUM Assembly | Eff_16 | 1.PI CD OOS 2.PI residue 3. RS OOS 4. PI THK abnormal 5. PI Crack 6. Abnormal PI profile 1. BR OOS 2. UBM dis-connnection/poor step coverage 3. UBM peeling 1.PR Under develop/ PR Over develop 2.PR CD out of spec 3. PR thickness OOS 4. Poor coating 1. Ni bubble, missing Ni 2.Bump Void OOS (deeper plating THK) 1. BR OOS 2. PI residue 3. PI damage 4. PI delamination 1.Glue residual 2.Bump crack 3.UBM crack 4.Md/UF delam | Pot_16
| 16 | UBM type / Thickness (um) |  | Ti1K/Cu5K/Ni2um Ti1K/Cu5K/Ni3um | Cap_17 | E16 | H16 | ETCH Assembly | Eff_17 | 1. Metal residue 2. BL OOS Bump Crack | Pot_17
| 17 | Bump composition |  | SnAg 1.8 SnAg 2.3 Eu | Cap_18 | E17 | H17 | 2RFL Assembly Reliability | Eff_18 | Irregular bump 1.Non-wetting 2.Bump bridge RT fail | Pot_18
Bump design | 18 | REPSV PI Opening Size(um) |  | 30~62 | Cap_19 | E18 | H18 | PI1 | Eff_19 | 1.PI CD OOS 2.RS OOS | Pot_19
| 19 | Min fianl metal trace to seal ring (um) |  | 6.7~20 | Cap_20 | E19 | H19 | PPHO | Eff_20 | PR bubble | Pot_20
| 20 | PI via opening bottom edge to pad psv. Edge (um) |  | 7~20 | Cap_21 | E20 | H20 | PI1 | Eff_21 | PI delamination | Pot_21
| 21 | PI edge inside seal ring (um) |  | 5~13 | Cap_22 | E21 | H21 | PI1 PPHO Assembly | Eff_22 | 1. PI delamination 2. PI Bubble PR bubble PI crack (pull out) | Pot_22
| 22 | PR thickness(um) |  | 30 50 | Cap_23 | E22 | H22 | PPHO PR STRIP | Eff_23 | 1.PR Under develop/ PR Over develop 2.PR CD out of spec 3. PR thickness OOS 4. Poor coating 1. PR residue on bump 2. PR residue around bump 3. Metal residue | Pot_23
| 23 | UBM Size(um) |  | 69~110 | Cap_24 | E23 | H23 | PPHO PLAT Assembly | Eff_24 | Under develop 1. Ni bubble (small UBM size ) 2.BC/BH OOS 3.Bump Void OOS( larger UBM size) 1.Bump bridge 2.Non-wetting 3.Bump crack | Pot_24
| 24 | UBM Overlap PSV (um) |  | 10~25 | Cap_25 | E24 | H24 | ETCH Assembly | Eff_25 | Pad damage Bump Crack | Pot_25
| 25 | UBM insdie final metal for FOC (um) |  | 3~7 | Cap_26 | E25 | H25 | Assembly | Eff_26 | Bump Crack | Pot_26
| 26 | UBM Plating Area(dm2) |  | 0.26~1.66 | Cap_27 | E26 | H26 | PPHO PLAT ETCH DESCUM | Eff_27 | Under develop 1.BC/BH OOS 2.Composition 3.Bump Void OOS Metal residue 1. Metal residue 2. BL OOS | Pot_27
| 27 | UBM Density (UBM Area/Die Area) |  | 2.52~25.06 | Cap_28 | E26 | H26 | PPHO PLAT ETCH DESCUM | Eff_28 | Under develop 1.BC/BH OOS 2.Composition 3.Bump Void OOS Metal residue 1. Metal residue 2. BL OOS | Pot_28
| 28 | Mushroom CD(um) |  | 105~173 | Cap_29 | E27 | H27 | ETCH DESCUM | Eff_29 | Metal residue 1. Metal residue 2. BL OOS | Pot_29
| 29 | Min Mushroom space(um) |  | 20~182 | Cap_30 | E28 | H28 | ETCH DESCUM | Eff_30 | Metal residue 1. Metal residue 2. BL OOS | Pot_30
| 30 | Min. Bump pitch (um) |  | 150~300 | Cap_31 | E29 | H29 | ETCH DESCUM Assembly Reliability | Eff_31 | Metal residue 1. Metal residue 2. BL OOS 1.Bump bridge 2. MD/UF Void RT fail | Pot_31
| 31 | Bump Height(um) |  | 70~100 | Cap_32 | E30 | H30 | ETCH CP Assembly | Eff_32 | Metal residue OS fail 1.Glue residual 2.Bump bridge 3.Non-wetting 4.MD/UF delam 5.MD/UF Void | Pot_32
| 32 | Bump Diameter(um) |  | - | Cap_33 | E31 | H31 | Assembly FT | Eff_33 | Bridge OS fail | Pot_33
| 33 | Bump Density (Bump Q'ty/Die Area) |  | 8.8~39.95 | Cap_34 | E32 | H32 | PPHO PLAT PR STRIP DESCUM Assembly Reliability | Eff_34 | Under develop 1.BC/BH OOS 2.Composition 3.Bump Void OOS 1. PR residue on bump 2. PR residue around bump 3. Metal residue 1. Metal residue 2. BL OOS 1.Coating /Debris residual 2.Flux residue 3.Bump crack 4. MD/UF void RT fail | Pot_34
| 34 | BH/UBM ratio |  | 0.85~1.1 | Cap_35 | E50 | H50 | PLAT | Eff_35 | BC/BH OOS | Pot_35
Outgoing criteria | 35 | LF Bump Ag% target |  | +/-0.5 | Cap_36 | E33 | H33 | Assembly FT Reliability | Eff_36 | 1.Non-wetting 2.Bump bridge OS fail RT fail | Pot_36
| 36 | Bump Height(um) |  | +/-10% | Cap_37 | E34 | H34 | CP Assembly FT | Eff_37 | OS fail Non Wetting OS fail | Pot_37
| 37 | Bump diameter |  | +/-10% | Cap_38 | E35 | H35 | Assembly FT | Eff_38 | Bridge OS fail | Pot_38
| 38 | Bump Coplanarity |  | <20 um | Cap_39 | E36 | H36 | CP Assembly FT | Eff_39 | OS fail Non Wetting OS fail | Pot_39
| 39 | Bump Shear Strenght |  | LF: >2.5 g/mil^2 | Cap_40 | E37 | H37 | Assembly Reliability | Eff_40 | Bump crack RT fail | Pot_40
| 40 | Bump void |  | <10 % | Cap_41 | E38 | H38 | Assembly FT | Eff_41 | Bump crack OS fail | Pot_41
| 41 | PI Rougness (Ra) |  | BGM3A:15~30nm | Cap_42 | E39 | H39 | Assembly FT | Eff_42 | 1.Glue residual 2.MD/UF Delam OS fail | Pot_42
| 42 | Bump Resistance (POR capability) |  |  | Cap_43 | E40 | H40 | CP FT | Eff_43 | Function fail Function fail | Pot_43
Metrology tool | 43 | August | Gross die | 10~50000 ea | Cap_44 | E51 | H51 | FV & 2D | Eff_44 | Alignment shift | Pot_44
|  |  | Expose pad | - | Cap_45 | E52 | H52 | FV & 2D | Eff_45 | 1st reject rate too high & defect escaped | Pot_45
|  |  | PSV1(PI1/PBO1) opening | 10~1000 | Cap_46 | E53 | H53 | 2D | Eff_46 | Defect escaped | Pot_46
|  |  | Bump diameter | 10~1000 | Cap_47 | E54 | H54 | FV | Eff_47 | Defect escaped | Pot_47
|  |  | Low SPEC of min RDL Width | 2 | Cap_48 | E55 | H55 | FV & 2D | Eff_48 | Defect escaped | Pot_48
|  |  | Low SPEC of min RDL Spacing | 2 | Cap_49 | E56 | H56 | FV & 2D | Eff_49 | Defect escaped | Pot_49
|  |  | Min RDL Width/Spacing pattern & location | - | Cap_50 | E57 | H57 | FV & 2D | Eff_50 | Defect escaped | Pot_50
| 44 | RVSI | Gross die | 10~50000 ea | Cap_51 | E58 | H58 | 3D | Eff_51 | Alignment shift | Pot_51
|  |  | Bump count per die | 1~500K | Cap_52 | E59 | H59 | 3D | Eff_52 | M/C limit | Pot_52
|  |  | Bump height | 3~1000 | Cap_53 | E60 | H60 | BH/Cop | Eff_53 | Data incorrect | Pot_53
|  |  | Bump diameter | 20~1000 | Cap_54 | E61 | H61 | BH/BD/Cop | Eff_54 | Data incorrect | Pot_54
| 45 | RS meter | Bump diameter | 25~1000 | Cap_55 | E62 | H62 | RS | Eff_55 | Data incorrect | Pot_55
| 46 | Void (X-ray) | Bump diameter | CS/DF site: 80~1000 CH site: 10~1000 | Cap_56 | E63 | H63 | Void | Eff_56 | Void escaped | Pot_56
| 47 | Bump shear | Bump diameter | 3~400 | Cap_57 | E64 | H64 | Shear test | Eff_57 | Data incorrect | Pot_57
| 48 | Bump pull | Bump diameter | 83-140, 200-326 | Cap_58 | E65 | H65 | Pull test | Eff_58 | Data incorrect | Pot_58
AB requirement | 49 | Bump to bump space |  | FCCSP >19um FCBGA>20um | Cap_59 | E41 | H41 | Assembly | Eff_59 | Bump bridge | Pot_59
| 50 | SMO |  | - | Cap_60 | E42 | H42 | -- | Eff_60 | -- | Pot_60
| 51 | UBM/SMO ratio |  | 0.85 - 1.1 | Cap_61 | E43 | H43 | Assembly | Eff_61 | Bump crack | Pot_61
Special Requirement | 52 | Process / Machine |  | - | Cap_62 |  |  | -- | Eff_62 | -- | Pot_62
| 53 | Material |  | - | Cap_63 |  |  | -- | Eff_63 | -- | Pot_63
| 54 | Measurement tool |  | - | Cap_64 |  |  | -- | Eff_64 | -- | Pot_64
| 55 | Reliability |  | - | Cap_65 |  |  | -- | Eff_65 | -- | Pot_65

## App Form功能
| Customer | AMD
| New Device | KINGSTON
| New Mask圖面設計繪製 (A) |  |  | APP01
| 設計修改 (A+B) |  |  | APP02 |  |  |  | Customer : |  | AMD-CPU | APP04 | 編輯時不可修改
| Study Case (A+C) |  |  | APP03 |  |  |  | Device : |  | KINGSTON | APP05 | 編輯時不可修改
APP06 | 申請日期 (REQUEST DATE) |  | 2015-04-27 |  |  |  | 希望完成日期 (SCHEDULE COMPLETION DATE) | [5 empty] | APP07
【A】設計條件/需求(Design Request)
| PKG type: | [8 empty] | APP08 | 編輯時不可修改
| Bump Height: |  |  |  | BH | APP09 | +/- | APP10 | %
| Bump Diameter PI anchor hole: |  |  |  | BD | APP11 | +/- | APP12 | %
|  |  |  | Material | THK-Value | THK | THK-Toler | Exp. Tool | Mask size | Field # per reticle | CD-Value | Design CD | CD-Toler | Size-Value | Feature Size | Size-Toler | Shape | Process type
|  |  |  | APP13 | APP14 |  | APP15 | APP16 | APP17 | APP18 | APP19 |  | APP20 | APP21 |  | APP22 | APP23 | APP24
| CD Design: |  |  | PI@Bump | 5 | +- | 1um | AP200/AP300 | 6" | 2 | 45 | +- | 1um | 45 | +- | 6um | Circle | Plating
|  |  |  | Plating@UBM | 3.9 | +- | 1.04um | MA300 | 14" |  | 75 | +- | 1um | 80 | +- | 4um | Circle | Plating
|  |  |  | APP25 | APP26 |  | APP27 | APP28 | APP29 | APP30 | APP31 |  | APP32 | APP33 |  | APP34 | APP35 | APP36
|  |  |  | APP37 | APP38 |  | APP39 | APP40 | APP41 | APP42 | APP43 |  | APP44 | APP45 |  | APP46 | APP47 | APP48
|  |  |  | APP49 | APP50 |  | APP51 | APP52 | APP53 | APP54 | APP55 |  | APP56 | APP57 |  | APP58 | APP59 | APP60
|  |  |  | APP61 | APP62 |  | APP63 | APP64 | APP65 | APP66 | APP67 |  | APP68 | APP69 |  | APP70 | APP71 | APP72
|  |  |  | APP73 | APP74 |  | APP75 | APP76 | APP77 | APP78 | APP79 |  | APP80 | APP81 |  | APP82 | APP83 | APP84
| Dummy Bump request (for plating +Aligner mask): |  |  | APP37 | 不需要dummy bumps |  |  | 需要dummy bumps |  | check Box
【B】修改參考(Design Reference)
| 1. Reference Mask drawing #: | [8 empty] | APP38
| 2. New Drawing No? |  |  |  | Yes No |  |  |  |  | APP39 | check Box
| 3. Change item | [8 empty] | APP40
【C】開發研究 (Study)
| 1. New structure | [8 empty] | APP41
| 2. New Bias | [8 empty] | APP42
| 3. Photoresist |  |  |  |  | P-photo |  | N-photo |  | APP43 | 下拉選單
| 4. Other | [8 empty] | APP44

## MamualForm功能
|  | 下拉選單 |  | 新增/刪除/修改/查詢功能
| NewCustomer | AMD-CPU
| NewDevice | KINGSTON
|  | New_Customer | New Device | UpdateTime
|  | AMD-CPU | KINGSTON | 2016/2/1 上午 10:08:03
New Customer |  | AMD-CPU
New Device |  | KINGSTON
Wafer PSV type / Thickness |  | SiN
PI type |  | HD4104
PI Thickness (um) |  | 5um
UBM type / Thickness (um) |  | Ti1K/Cu3K/Ni3.5um
PR thickness(um) |  | 50
UBM insdie final metal for FOC (um) |  | NA
UBM Plating Area(dm2) |  | 1.336
UBM Density (UBM Area/Die Area) |  | 20.08%
Mushroom CD(um) |  | 106
Min Mushroom space(um) |  | 44
Bump Density (Bump Q'ty/Die Area) |  | 39.95
BH/UBM ratio |  | 1
Bump Coplanarity |  | <20 um
Bump Shear Strenght |  | LF: >2.5 g/mil^2
Bump void |  | <10 %
PI Rougness (Ra) |  | BGM3A:15~30nm
August | Gross die () | 294
| Expose pad | NA
RVSI | Gross die | 294
Bump to bump space (um) |  | 60
SMO (um) |  | 80
UBM/SMO ratio |  | 1

## PORForm功能
POR Golden Condition
| PKG |  | EP FOC-12-LF | RVSI(Y/N) |  | Y
| Wafer Tech.(nm) |  | 40 | Customer |  | UMC
| FAB |  | UMC | Production Site |  | CS
| Wafer PSV type / Thickness |  | SiN
Device | *Production Site | *PKG | *Wafer Tech.(nm) | *FAB | *Wafer PSV type / Thickness | *RVSI(Y/N) | *Customer
BCM4334YUB1 | CS | EP REPSV-12-LF | 40 | UMC | SiN | Y | UMC
New POR

## DIF_Q&R_DRC ExcelImport
*Import Excel Function:
1.Import Excel
2.查詢功能
3.DB Table: npiimportdata

## EPTRP_SelectPOR
POR Golden Condition
Production Site |  | EP FOC-12-LF | Wafer PSV type / Thickness |  | Y
PKG |  | 40 | RVSI(Y/N) |  | UMC
Wafer Tech.(nm) |  | UMC | Customer |  | CS
FAB |  | SiN
Customer
RVSI(Y/N)
Device | *Production Site | *PKG | *Wafer Tech.(nm) | *FAB | *Wafer PSV type / Thickness | *RVSI(Y/N) | *Customer
KINGSTON-LUBM | CS | EP REPSV-12-LF | 40 | UMC | SiN | Y | UMC

## EP_TRA比對總表
POR Golden
|  | POR Device |  | KINGSTON-LUBM
New Device
|  | Customer |  | AMD-CPU
|  | New Device |  | KINGSTON
Key item |  |  |  | Capability | POR (Baseline) | New Device | Gap (Y/N) | Package/ProcessTRA
[8 empty] | Effect stage | Potential Effect | TRA Lv. | Recommend action | Owner | Due Date
PROD |  |  |  | - | POR_15 |  | = | Eff_01 | Pot_01
Device Information | 1 | Customer |  | - | POR_14 | DIF! D4 | no need | Eff_02 | Pot_02
| 2 | Device |  | - | POR_17 | DIF! D5 | no need | Eff_03 | Pot_03
| 3 | Die size(mm*mm) |  | 4*4~23*23 | POR_18 | DIF! D19 x DIF! G19 | = | Eff_04 | Pot_04
| 4 | C/P probe card type |  | Vertical probe Membrane | POR_46 | Q&R! D16 | = | Eff_05 | Pot_05
| 5 | Probing on bump pad (Y/N) |  | Not Allowed | POR_24 | Q&R! D13 | = | Eff_06 | Pot_06
Wafer Information | 6 | Wafer Fab |  | TSMC,UMC,GF,SMIC | POR_04 | Q&R! D7 | = | Eff_07 | Pot_07
| 7 | Wafer tech.(nm) |  | 28~130 | POR_03 | Q&R! D8 | = | Eff_08 | Pot_08
| 8 | Low K Type |  | ELK | POR_12 | Q&R! D9 | = | Eff_09 | Pot_09
| 9 | Final Metal Pad type |  | Al Cu | POR_20 | DIF! F11 | = | Eff_10 | Pot_10
| 10 | RV hole(Y/N) |  | Not Allowed | POR_23 | Q&R! D11 | = | Eff_11 | Pot_11
| 11 | Wafer PSV type / Thickness |  | SiN | POR_21 | Man_01 | = | Eff_12 | Pot_12
| 12 | Seal-Ring Protected by SiN (Y/N) |  | Y | POR_25 | Q&R! D12 | = | Eff_13 | Pot_13
Bump structure | 13 | PKG Type |  | EP REPSV-12-EU EP REPSV-12-LF EP FOC-12-EU EP FOC-12-LF EP REPSV-8-LF | POR_02 | APP_08 | no need | Eff_14 | Pot_14
| 14 | PI type |  | HD4104 | POR_26 | Man_02 | = | Eff_15 | Pot_15
| 15 | PI Thickness (um) |  | 5um | POR_55 | Man_03 | = | Eff_16 | Pot_16
| 16 | UBM type / Thickness (um) |  | Ti1K/Cu5K/Ni2um Ti1K/Cu5K/Ni3um | POR_16 | Man_04 | = | Eff_17 | Pot_17
| 17 | Bump composition |  | SnAg 1.8 SnAg 2.3 Eu | POR_33 | Q&R! D26 | = | Eff_18 | Pot_18
Bump design | 18 | REPSV PI Opening Size(um) |  | 30~62 | POR_30 | APP_21 | = | Eff_19 | Pot_19
| 19 | Min fianl metal trace to seal ring (um) |  | 6.7~20 | NA | DRC! F38 | = | Eff_20 | Pot_20
| 20 | PI via opening bottom edge to pad psv. Edge (um) |  | 7~20 | POR_31 | DRC! F39 | = | Eff_21 | Pot_21
| 21 | PI edge inside seal ring (um) |  | 5~13 | POR_32 | DRC! F35 | = | Eff_22 | Pot_22
| 22 | PR thickness(um) |  | 30 50 | POR_13 | Man_05 | = | Eff_23 | Pot_23
| 23 | UBM Size(um) |  | 69~110 | POR_29 | APP_33 | = | Eff_24 | Pot_24
| 24 | UBM Overlap PSV (um) |  | 10~25 | POR_27 | DRC! F34 | = | Eff_25 | Pot_25
| 25 | UBM insdie final metal for FOC (um) |  | 3~7 | POR_28 | Man_06 | = | Eff_26 | Pot_26
| 26 | UBM Plating Area(dm2) |  | 0.26~1.66 | POR_34 | Man_07 | = | Eff_27 | Pot_27
| 27 | UBM Density (UBM Area/Die Area) |  | 2.52~25.06 | POR_50 | Man_08 | = | Eff_28 | Pot_28
| 28 | Mushroom CD(um) |  | 105~173 | POR_44 | Man_09 | = | Eff_29 | Pot_29
| 29 | Min Mushroom space(um) |  | 20~182 | POR_43 | Man_10 | = | Eff_30 | Pot_30
| 30 | Min. Bump pitch (um) |  | 150~300 | POR_19 | DIF! D29 | = | Eff_31 | Pot_31
| 31 | Bump Height(um) |  | 70~100 | POR_35 | APP_09 | = | Eff_32 | Pot_32
| 32 | Bump Diameter(um) |  | - | POR_45 | APP_11 | = | Eff_33 | Pot_33
| 33 | Bump Density (Bump Q'ty/Die Area) |  | 8.8~39.95 | POR_22 | Man_11 | = | Eff_34 | Pot_34
| 34 | BH/UBM ratio |  | 0.85~1.1 | 1 | Man_12 | = | Eff_35 | Pot_35
Outgoing criteria | 35 | LF Bump Ag% target |  | +/-0.5 |  | Q&R! E26 | = | Eff_36 | Pot_36
| 36 | Bump Height(um) |  | +/-10% |  | APP_10 | = | Eff_37 | Pot_37
| 37 | Bump diameter |  | +/-10% |  | APP_12 | = | Eff_38 | Pot_38
| 38 | Bump Coplanarity |  | <20 um |  | Man_13 | = | Eff_39 | Pot_39
| 39 | Bump Shear Strenght |  | LF: >2.5 g/mil^2 |  | Man_14 | = | Eff_40 | Pot_40
| 40 | Bump void |  | <10 % |  | Man_15 | = | Eff_41 | Pot_41
| 41 | PI Rougness (Ra) |  | BGM3A:15~30nm |  | Man_16 | = | Eff_42 | Pot_42
| 42 | Bump Resistance (POR capability) |  | POR_10 |  | Q&R! D30 | = | Eff_43 | Pot_43
Metrology tool | 43 | August | Gross die | 10~50000 ea | 58~25747 ea | Man_17 | Man_17>=58 and Man_17<=25747 =>N | Eff_44 | Pot_44
|  |  | Expose pad | - | No | Man_18 | = | Eff_45 | Pot_45
|  |  | PSV1(PI1/PBO1) opening | 10~1000 | 22~240 | APP_21 | APP_21>=22 and APP_21<=240 =>N | Eff_46 | Pot_46
|  |  | Bump diameter | 10~1000 | 84~127 | APP_11 | APP_11>=84 and APP_11<=127 =>N | Eff_47 | Pot_47
|  |  | Low SPEC of min RDL Width | 2 | 10~78 | - | ?? | Eff_48 | Pot_48
|  |  | Low SPEC of min RDL Spacing | 2 | 10~29 | - | ?? | Eff_49 | Pot_49
|  |  | Min RDL Width/Spacing pattern & location | - | - | - | = | Eff_50 | Pot_50
| 44 | RVSI | Gross die | 10~50000 ea | 58~25747 ea | Man_19 | Man_19>=58 and Man_19<=25747 =>N | Eff_51 | Pot_51
|  |  | Bump count per die | 1~500K | 172~18510 | DIF! D30 | DIF!D30>=172 and DIF!D30<=18510 =>N | Eff_52 | Pot_52
|  |  | Bump height | 3~1000 | 65~108 | APP_09 | APP_09>=65 and APP_09<=108 =>N | Eff_53 | Pot_53
|  |  | Bump diameter | 20~1000 | 84~138 | APP_11 | APP_11>=84 and APP_11<=138 =>N | Eff_54 | Pot_54
| 45 | RS meter | Bump diameter | 25~1000 | 30~326 | APP_11 | APP_11>=30 and APP_11<=326 =>N | Eff_55 | Pot_55
| 46 | Void (X-ray) | Bump diameter | CS/DF site: 80~1000 CH site: 10~1000 | CS/DF: 80~326 CH: 30~326 | APP_11 | APP_11>=30 and APP_11<=326 =>N | Eff_56 | Pot_56
| 47 | Bump shear | Bump diameter | 3~400 | 23~326 | APP_11 | APP_11>=23 and APP_11<=326 =>N | Eff_57 | Pot_57
| 48 | Bump pull | Bump diameter | 83-140, 200-326 | 83-140, 200-326 | APP_11 | ((APP_11>=83 and APP_11<=140) or (APP_11>=200 and APP_11<=326)) =>N | Eff_58 | Pot_58
AB requirement | 49 | Bump to bump space |  | FCCSP >19um FCBGA>20um | POR_48 | Man_20 | = | Eff_59 | Pot_59
| 50 | SMO |  | - | POR_49 | Man_21 | = | Eff_60 | Pot_60
| 51 | UBM/SMO ratio |  | 0.85 - 1.1 | POR_36 | Man_22 | = | Eff_61 | Pot_61
Special Requirement | 52 | Process / Machine |  | - | POR_38 | NA | = | Eff_62 | Pot_62
| 53 | Material |  | - | POR_39 | NA | = | Eff_63 | Pot_63
| 54 | Measurement tool |  | - | POR_40 | NA | = | Eff_64 | Pot_64
| 55 | Reliability |  | - | POR_41 | NA | = | Eff_65 | Pot_65
選擇POR Golden

## 查詢 EP_TRA
| Customer |  | AMD-CPU
| New Device |  | KINGSTON
| POR Golden |  | KINGSTON-LUBM
| Version |  | AMD-CPU_KINGSTON_Ver001
| Creater Date |  | 20151203110533
| Key item |  |  |  | Capability | POR (Baseline) | New Device | Gap (Y/N) | Package/ProcessTRA
[9 empty] | Effect stage | Potential Effect | TRA Lv. | Recommend action | Owner | Due Date
| PROD |  |  |  | - | POR_15 |  | = | Eff_01 | Pot_01
| Device Information | 1 | Customer |  | - | POR_14 | DIF! D4 | no need | Eff_02 | Pot_02
|  | 2 | Device |  | - | POR_17 | DIF! D5 | no need | Eff_03 | Pot_03
|  | 3 | Die size(mm*mm) |  | 4*4~23*23 | POR_18 | DIF! D19 x DIF! G19 | = | Eff_04 | Pot_04
|  | 4 | C/P probe card type |  | Vertical probe Membrane | POR_46 | Q&R! D16 | = | Eff_05 | Pot_05
|  | 5 | Probing on bump pad (Y/N) |  | Not Allowed | POR_24 | Q&R! D13 | = | Eff_06 | Pot_06
| Wafer Information | 6 | Wafer Fab |  | TSMC,UMC,GF,SMIC | POR_04 | Q&R! D7 | = | Eff_07 | Pot_07
|  | 7 | Wafer tech.(nm) |  | 28~130 | POR_03 | Q&R! D8 | = | Eff_08 | Pot_08
|  | 8 | Low K Type |  | ELK | POR_12 | Q&R! D9 | = | Eff_09 | Pot_09
|  | 9 | Final Metal Pad type |  | Al Cu | POR_20 | DIF! F11 | = | Eff_10 | Pot_10
|  | 10 | RV hole(Y/N) |  | Not Allowed | POR_23 | Q&R! D11 | = | Eff_11 | Pot_11
|  | 11 | Wafer PSV type / Thickness |  | SiN | POR_21 | Man_01 | = | Eff_12 | Pot_12
|  | 12 | Seal-Ring Protected by SiN (Y/N) |  | Y | POR_25 | Q&R! D12 | = | Eff_13 | Pot_13
| Bump structure | 13 | PKG Type |  | EP REPSV-12-EU EP REPSV-12-LF EP FOC-12-EU EP FOC-12-LF EP REPSV-8-LF | POR_02 | APP_08 | no need | Eff_14 | Pot_14
|  | 14 | PI type |  | HD4104 | POR_26 | Man_02 | = | Eff_15 | Pot_15
|  | 15 | PI Thickness (um) |  | 5um | POR_55 | Man_03 | = | Eff_16 | Pot_16
|  | 16 | UBM type / Thickness (um) |  | Ti1K/Cu5K/Ni2um Ti1K/Cu5K/Ni3um | POR_16 | Man_04 | = | Eff_17 | Pot_17
|  | 17 | Bump composition |  | SnAg 1.8 SnAg 2.3 Eu | POR_33 | Q&R! D26 | = | Eff_18 | Pot_18
| Bump design | 18 | REPSV PI Opening Size(um) |  | 30~62 | POR_30 | APP_21 | = | Eff_19 | Pot_19
|  | 19 | Min fianl metal trace to seal ring (um) |  | 6.7~20 | NA | DRC! F38 | = | Eff_20 | Pot_20
|  | 20 | PI via opening bottom edge to pad psv. Edge (um) |  | 7~20 | POR_31 | DRC! F39 | = | Eff_21 | Pot_21
|  | 21 | PI edge inside seal ring (um) |  | 5~13 | POR_32 | DRC! F35 | = | Eff_22 | Pot_22
|  | 22 | PR thickness(um) |  | 30 50 | POR_13 | Man_05 | = | Eff_23 | Pot_23
|  | 23 | UBM Size(um) |  | 69~110 | POR_29 | APP_33 | = | Eff_24 | Pot_24
|  | 24 | UBM Overlap PSV (um) |  | 10~25 | POR_27 | DRC! F34 | = | Eff_25 | Pot_25
|  | 25 | UBM insdie final metal for FOC (um) |  | 3~7 | POR_28 | Man_06 | = | Eff_26 | Pot_26
|  | 26 | UBM Plating Area(dm2) |  | 0.26~1.66 | POR_34 | Man_07 | = | Eff_27 | Pot_27
|  | 27 | UBM Density (UBM Area/Die Area) |  | 2.52~25.06 | POR_50 | Man_08 | = | Eff_28 | Pot_28
|  | 28 | Mushroom CD(um) |  | 105~173 | POR_44 | Man_09 | = | Eff_29 | Pot_29
|  | 29 | Min Mushroom space(um) |  | 20~182 | POR_43 | Man_10 | = | Eff_30 | Pot_30
|  | 30 | Min. Bump pitch (um) |  | 150~300 | POR_19 | DIF! D29 | = | Eff_31 | Pot_31
|  | 31 | Bump Height(um) |  | 70~100 | POR_35 | APP_09 | = | Eff_32 | Pot_32
|  | 32 | Bump Diameter(um) |  | - | POR_45 | APP_11 | = | Eff_33 | Pot_33
|  | 33 | Bump Density (Bump Q'ty/Die Area) |  | 8.8~39.95 | POR_22 | Man_11 | = | Eff_34 | Pot_34
|  | 34 | BH/UBM ratio |  | 0.85~1.1 | 1 | Man_12 | = | Eff_35 | Pot_35
| Outgoing criteria | 35 | LF Bump Ag% target |  | +/-0.5 |  | Q&R! E26 | = | Eff_36 | Pot_36
|  | 36 | Bump Height(um) |  | +/-10% |  | APP_10 | = | Eff_37 | Pot_37
|  | 37 | Bump diameter |  | +/-10% |  | APP_12 | = | Eff_38 | Pot_38
|  | 38 | Bump Coplanarity |  | <20 um |  | Man_13 | = | Eff_39 | Pot_39
|  | 39 | Bump Shear Strenght |  | LF: >2.5 g/mil^2 |  | Man_14 | = | Eff_40 | Pot_40
|  | 40 | Bump void |  | <10 % |  | Man_15 | = | Eff_41 | Pot_41
|  | 41 | PI Rougness (Ra) |  | BGM3A:15~30nm |  | Man_16 | = | Eff_42 | Pot_42
|  | 42 | Bump Resistance (POR capability) |  | POR_10 |  | Q&R! D30 | = | Eff_43 | Pot_43
43 | Metrology tool | 43 | August | Gross die | 10~50000 ea | 58~25747 ea | Man_17 | Man_17>=58 and Man_17<=25747 =>N | Eff_44 | Pot_44
44 |  |  |  | Expose pad | - | No | Man_18 | = | Eff_45 | Pot_45
45 |  |  |  | PSV1(PI1/PBO1) opening | 10~1000 | 22~240 | APP_21 | APP_21>=22 and APP_21<=240 =>N | Eff_46 | Pot_46
46 |  |  |  | Bump diameter | 10~1000 | 84~127 | APP_11 | APP_11>=84 and APP_11<=127 =>N | Eff_47 | Pot_47
47 |  |  |  | Low SPEC of min RDL Width | 2 | 10~78 | - | ?? | Eff_48 | Pot_48
48 |  |  |  | Low SPEC of min RDL Spacing | 2 | 10~29 | - | ?? | Eff_49 | Pot_49
49 |  |  |  | Min RDL Width/Spacing pattern & location | - | - | - | = | Eff_50 | Pot_50
50 |  | 44 | RVSI | Gross die | 10~50000 ea | 58~25747 ea | Man_19 | Man_19>=58 and Man_19<=25747 =>N | Eff_51 | Pot_51
51 |  |  |  | Bump count per die | 1~500K | 172~18510 | DIF! D30 | DIF!D30>=172 and DIF!D30<=18510 =>N | Eff_52 | Pot_52
52 |  |  |  | Bump height | 3~1000 | 65~108 | APP_09 | APP_09>=65 and APP_09<=108 =>N | Eff_53 | Pot_53
53 |  |  |  | Bump diameter | 20~1000 | 84~138 | APP_11 | APP_11>=84 and APP_11<=138 =>N | Eff_54 | Pot_54
54 |  | 45 | RS meter | Bump diameter | 25~1000 | 30~326 | APP_11 | APP_11>=30 and APP_11<=326 =>N | Eff_55 | Pot_55
55 |  | 46 | Void (X-ray) | Bump diameter | CS/DF site: 80~1000 CH site: 10~1000 | CS/DF: 80~326 CH: 30~326 | APP_11 | APP_11>=30 and APP_11<=326 =>N | Eff_56 | Pot_56
56 |  | 47 | Bump shear | Bump diameter | 3~400 | 23~326 | APP_11 | APP_11>=23 and APP_11<=326 =>N | Eff_57 | Pot_57
57 |  | 48 | Bump pull | Bump diameter | 83-140, 200-326 | 83-140, 200-326 | APP_11 | ((APP_11>=83 and APP_11<=140) or (APP_11>=200 and APP_11<=326)) =>N | Eff_58 | Pot_58
| AB requirement | 49 | Bump to bump space |  | FCCSP >19um FCBGA>20um | POR_48 | Man_20 | = | Eff_59 | Pot_59
|  | 50 | SMO |  | - | POR_49 | Man_21 | = | Eff_60 | Pot_60
|  | 51 | UBM/SMO ratio |  | 0.85 - 1.1 | POR_36 | Man_22 | = | Eff_61 | Pot_61
| Special Requirement | 52 | Process / Machine |  | - | POR_38 | NA | = | Eff_62 | Pot_62
|  | 53 | Material |  | - | POR_39 | NA | = | Eff_63 | Pot_63
|  | 54 | Measurement tool |  | - | POR_40 | NA | = | Eff_64 | Pot_64
|  | 55 | Reliability |  | - | POR_41 | NA | = | Eff_65 | Pot_65

## PreNPI流程
客戶提供 | 光罩設計 | PIE
DIF | DRC | ApplicationForm
Q&R |  | Mamual Form
POR Golden
DIF
Q&R
DRC
Application &Mamual Form
PIE: POR Seletction Rule
New Customer/Device
1.進行比對產生EP_TRA
2.將有Gap的項目進行關聯註解
1.將比對結果儲存,將建立本次:Customer_NewDevice_VerNNN
(NNN: 流水號 001~999)
2.要修改已儲存的比對結果,必須重新比對然後儲存系統進版
3.當POR Golden或是重新匯入有修改的DIF/Q&R/DCR/APP/Mamual
內容時,必須重新比對然後儲存系統進版
重新挑選POR Golden
系統比對結果
產生EA_TRA
唯一的POR Golden
1.根據唯一的POR Golden內的13項條件,比對NewDevice內容
2.確認New Device 項目完整(依據13 Rule)
DIF/Q&R/DRC/App/Mamual Form的內容
New Customer/Device內容不足
Review New Device資料

## Sheet1
PordSite | PKG | WaferTech | FAB | WaferType | Tietching | YN | PI Rougness | LK | PR Thick | Customer | Device | Process
CS | EP FOC-12-EU | 16 | GF | SiN | DHF | Y | BGM2.7~15nm | E Low K | 30 | AMD | GK106 | Plating
CH | EP FOC-12-LF | 28 | SMIC | TSMC PI | T89 | N | BGM3A:15~30nm | ELK | 50 | Avago | GK107 | Sputter
DF | EP REPSV-12-EU | 40 | TSMC |  | T89+DHF |  | NA | Low K |  | Avago-LS | AXM3500A0
ZK | EP REPSV-12-LF | 45 | UMC |  |  |  | SAD:1~8% | Non-Low K |  | ESILICON | BCM3142C-LF
| EP REPSV-8-LF | 65 | [7 empty] | GLOBALFOUNDIES | BCM4325YD3
|  | 90 | [7 empty] | Infineon | BCM4334YUB1
|  | 130 | [7 empty] | LSI | BCM43352YCB1
[10 empty] | Magnum | BCM43451YUB0
[10 empty] | Marvell | BCM6362B1
[10 empty] | MEDATEK | BCM7125E
[10 empty] | NV | BCM7231
[10 empty] | Parade | BCM88130B
[10 empty] | PARROT | DP685
[10 empty] | Sigma Design | DE3005
[10 empty] | SMIC | Everest
[10 empty] | SPIL | Fusion
[10 empty] | TSMC-QCT | GM108
[10 empty] | UMC | GM107
[10 empty] | VeriSilicon-CN | KINGSTON-LUBM
[10 empty] | XILINX | M8824U
XC6VLX365T

## Sheet2
*1 | ProductionSite | CS | 15 | PORD | 12-BP-FOC-EP-EU-TCN-9D-04 | 29 | UBMSize | 80 | 43 | Mushroon Space | 34
*2 | PKG | EP FOC-12-EU | 16 | UBMType/Thickness | Ti3K/Cu3K/Cu5/Ni2um | 30 | REPSVPIOpeningSize | NA | 44 | MushroonCD | 135
*3 | WaferTech(nm) | 40 | 17 | Device | BCM7125E | 31 | PIviaOpening | NA | 45 | Bump | 100
*4 | FAB | UMC | 18 | DieSize | 9.21*10.63 | 32 | PIEdgeInside | 10 | 46 | C/PProbe | Vertical probe
*5 | WaferPSVType/Thickness | SiN | 19 | MinBumpPitch | 169.2 | 33 | BumpType | Plated 63Sn/37Pb | 47 | MinFinalMetalPadToSealRing
6 | PRType | AZ | 20 | FinalMetalPadType | Al | 34 | UBMPlatingArea | 0.42 | 48 | BumpToBumpSpace | 69.2
7 | TietchingChemical | DHF | 21 | WaferPSVTypeThickness | SiN | 35 | BumpHeight | 80 | 49 | SMO | 80
8 | TinShellBake | N | 22 | BumpDensity | 12.81 | 36 | UBM/SMORatio | 1 | 50 | UBMDensity | 0.0644
9 | PIrougness | BGM3A15~30nm | 23 | RVHoleOnAlPad | N | 37 | BH/UBMRatio | 1 | 51 | DieSizeX | 9.21
10 | BumpResistance | <30 mohm | 24 | ProbingOnPad | N | 38 | Process/Machine | NA | 52 | DieSizeY | 10.63
*11 | RVSI(Y/N) | N | 25 | SelRingProtectedBySiN | Y | 39 | Material | NA | 53 | BumpCount | 1254
12 | LowK | Low K | 26 | PassivationType | HD4104 | 40 | MeasurementTool | NA | 54 | CornerUBMDensity
13 | PRThickness | 50 | 27 | UBMOverlapPSV | 12 | 41 | Raliability | NA | 55 | PassivationThickness | 5um
*14 | Customer | UMC | 28 | UBMInsdieFinalMetalForFOC | 4 | 42 | Remark

## EP_TRA Table
npiEPTRAVer_Main | [5 empty] | npiEPTRAVer_POR |  |  |  |  | npiPOR | [7 empty] | npiEPTRAVer_New | [5 empty] | New Device |  | npiEPTRAVer_Gap | [5 empty] | npieptraver_cap |  |  |  |  | npieptraver_effect |  |  |  |  | npieptraver_portential
Name | PK | Null | Data Type | Length |  | Name | PK | Null | Data Type | Length | 資料行名稱 | PK | 資料型態 | 允許Null |  | POR (Baseline) |  |  | Name | PK | Null | Data Type | Length |  |  |  | Name | PK | Null | Data Type | Length |  | Name | PK | Null | Data Type | Length | Name | PK | Null | Data Type | Length | Name | PK | Null | Data Type | Length
Ver_Name | V |  | varchar | 80 |  | Ver_Name | V |  | varchar | 50 | Por_Customer | V | varchar(30) | [5 empty] | Ver_Name | V |  | varchar | 50 | 40 |  | Ver_NEW_1 | Ver_Name | V |  | varchar | 50 |  | Ver_Name | V |  | varchar | 50 | Ver_Name | V |  | varchar | 50 | Ver_Name | V |  | varchar | 50
Ver_No | V |  | varchar | 3 |  | UpdateTime |  |  | Datetime |  | Por_Device | V | varchar(30) |  | 40 | POR_15 | Ver_POR_1 |  | UpdateTime |  |  | Datatime |  | 30 | DIF! D4 | Ver_NEW_2 | UpdateTime |  |  | Datatime |  |  | UpdateTime |  |  | Datatime |  | UpdateTime |  |  | Datatime |  | UpdateTime |  |  | Datatime
CreateTime |  |  | Datatime |  |  | UserName |  |  | varchar | 10 | SType | V | varchar(5) |  | 20 | POR_14 | Ver_POR_2 |  | UserName |  |  | varchar | 10 | 30 | DIF! D5 | Ver_NEW_3 | UserName |  |  | varchar | 10 | CIM | UserName |  |  | varchar | 10 | UserName |  |  | varchar | 10 | UserName |  |  | varchar | 10
UpdateTime |  |  | Datatime |  |  | Ver_Status |  |  | varchar | 1 | UpdateTime |  | Datatime |  | 30 | POR_17 | Ver_POR_3 |  | Ver_Status |  |  | varchar | 1 | 30 | DIF! D19 x DIF! G19 | Ver_NEW_4 | LastName |  |  | varchar | 10 | CIM | LastName |  |  | varchar | 10 | LastName |  |  | varchar | 10 | LastName |  |  | varchar | 10
UserName |  |  | varchar | 10 | Y/N | Ver_POR_1 |  | V | varchar | 40 | npiUser |  | varchar(10) | V | 15 | POR_18 | Ver_POR_4 |  | Ver_NEW_1 |  | V | varchar | 40 | 30 | Q&R! D16 | Ver_NEW_5 | Ver_Status |  |  | varchar | 1 |  | Ver_Status |  |  | varchar | 1 | Ver_Status |  |  | varchar | 1 | Ver_Status |  |  | varchar | 1
Ver_Status |  |  | varchar | 1 | Y/N | Ver_POR_2 |  | V | varchar | 20 | Por_Status |  | varchar(1) | V | 20 | POR_46 | Ver_POR_5 |  | Ver_NEW_2 |  | V | varchar | 30 | 30 | Q&R! D13 | Ver_NEW_6 | Ver_Gap1 |  |  | varchar | 1
LV_Setting_Status |  |  | varchar | 1 |  | Ver_POR_3 |  | V | varchar | 30 | Por_01 | V | varchar(5) |  | 1 | POR_24 | Ver_POR_6 |  | Ver_NEW_3 |  | V | varchar | 30 | 30 | Q&R! D7 | Ver_NEW_7 | Ver_Gap2 |  |  | varchar | 1
Ver_POR_Customer |  |  | varchar | 30 |  | Ver_POR_4 |  | V | varchar | 15 | Por_02 |  | varchar(25) | V | 10 | POR_04 | Ver_POR_7 |  | Ver_NEW_4 |  | V | varchar | 30 | 30 | Q&R! D8 | Ver_NEW_8 | Ver_Gap3 |  |  | varchar | 1
Ver_POR_Device |  |  | varchar | 30 |  | Ver_POR_5 |  | V | varchar | 20 | Por_03 |  | varchar(5) | V | 5 | POR_03 | Ver_POR_8 |  | Ver_NEW_5 |  | V | varchar | 30 | 30 | Q&R! D9 | Ver_NEW_9 | Ver_Gap4 |  |  | varchar | 1
Ver_POR_Site |  |  | varchar | 5 |  | Ver_POR_6 |  | V | varchar | 1 | Por_04 |  | varchar(10) | V | 15 | POR_12 | Ver_POR_9 |  | Ver_NEW_6 |  | V | varchar | 30 | 30 | DIF! F11 | Ver_NEW_10 | Ver_Gap5 |  |  | varchar | 1
Ver_POR_PKG |  |  | varchar | 25 |  | Ver_POR_7 |  | V | varchar | 10 | Por_05 |  | varchar(10) | V | 5 | POR_20 | Ver_POR_10 |  | Ver_NEW_7 |  | V | varchar | 30 | 30 | Q&R! D11 | Ver_NEW_11 | Ver_Gap6 |  |  | varchar | 1
Ver_POR_WT |  |  | varchar | 5 |  | Ver_POR_8 |  | V | varchar | 5 | Por_06 |  | varchar(5) | V | 1 | POR_23 | Ver_POR_11 |  | Ver_NEW_8 |  | V | varchar | 30 | 30 | Man_01 | Ver_NEW_12 | Ver_Gap7 |  |  | varchar | 1
Ver_POR_FAB |  |  | varchar | 10 |  | Ver_POR_9 |  | V | varchar | 15 | Por_07 |  | varchar(10) | V | 15 | POR_21 | Ver_POR_12 |  | Ver_NEW_9 |  | V | varchar | 30 | 30 | Q&R! D12 | Ver_NEW_13 | Ver_Gap8 |  |  | varchar | 1
Ver_POR_PSV |  |  | varchar | 10 |  | Ver_POR_10 |  | V | varchar | 5 | Por_08 |  | varchar(1) | V | 1 | POR_25 | Ver_POR_13 |  | Ver_NEW_10 |  | V | varchar | 30 | 30 | APP_08 | Ver_NEW_14 | Ver_Gap9 |  |  | varchar | 1
Ver_POR_RVSI |  |  | varchar | 1 |  | Ver_POR_11 |  | V | varchar | 1 | Por_09 |  | varchar(20) | V | 25 | POR_02 | Ver_POR_14 |  | Ver_NEW_11 |  | V | varchar | 30 | 20 | Man_02 | Ver_NEW_15 | Ver_Gap10 |  |  | varchar | 1
Ver_New_Customer |  |  | varchar | 30 |  | Ver_POR_12 |  | V | varchar | 15 | Por_10 |  | varchar(10) | V | 10 | POR_26 | Ver_POR_15 |  | Ver_NEW_12 |  | V | varchar | 30 | 15 | Man_03 | Ver_NEW_16 | Ver_Gap11 |  |  | varchar | 1
Ver_New_Device |  |  | varchar | 30 |  | Ver_POR_13 |  | V | varchar | 1 | Por_11 |  | varchar(1) | V | 5 | POR_55 | Ver_POR_16 |  | Ver_NEW_13 |  | V | varchar | 30 | 60 | Man_04 | Ver_NEW_17 | Ver_Gap12 |  |  | varchar | 1
[6 empty] | Ver_POR_14 |  | V | varchar | 25 | Por_12 |  | varchar(15) | V | 30 | POR_16 | Ver_POR_17 |  | Ver_NEW_14 |  | V | varchar | 30 | 30 | Q&R! D26 | Ver_NEW_18 | Ver_Gap13 |  |  | varchar | 1
[6 empty] | Ver_POR_15 |  | V | varchar | 10 | Por_13 |  | varchar(5) | V | 20 | POR_33 | Ver_POR_18 |  | Ver_NEW_15 |  | V | varchar | 20 | 30 | APP_21 | Ver_NEW_19 | Ver_Gap14 |  |  | varchar | 1
[6 empty] | Ver_POR_16 |  | V | varchar | 5 | Por_14 |  | varchar(20) | V | 15 | POR_30 | Ver_POR_19 |  | Ver_NEW_16 |  | V | varchar | 15 | 30 | DRC! F38 | Ver_NEW_20 | Ver_Gap15 |  |  | varchar | 1
[6 empty] | Ver_POR_17 |  | V | varchar | 30 | Por_15 |  | varchar(40) | V | 5 | NA | Ver_POR_20 |  | Ver_NEW_17 |  | V | varchar | 60 | 30 | DRC! F39 | Ver_NEW_21 | Ver_Gap16 |  |  | varchar | 1
[6 empty] | Ver_POR_18 |  | V | varchar | 20 | Por_16 |  | varchar(30) | V | 25 | POR_31 | Ver_POR_21 |  | Ver_NEW_18 |  | V | varchar | 30 | 30 | DRC! F35 | Ver_NEW_22 | Ver_Gap17 |  |  | varchar | 1
[6 empty] | Ver_POR_19 |  | V | varchar | 15 | Por_17 |  | varchar(30) | V | 25 | POR_32 | Ver_POR_22 |  | Ver_NEW_19 |  | V | varchar | 30 | 15 | Man_05 | Ver_NEW_23 | Ver_Gap18 |  |  | varchar | 1
[6 empty] | Ver_POR_20 |  | V | varchar | 5 | Por_18 |  | varchar(15) | V | 5 | POR_13 | Ver_POR_23 |  | Ver_NEW_20 |  | V | varchar | 30 | 30 | APP_33 | Ver_NEW_24 | Ver_Gap19 |  |  | varchar | 1
[6 empty] | Ver_POR_21 |  | V | varchar | 25 | Por_19 |  | varchar(10) | V | 5 | POR_29 | Ver_POR_24 |  | Ver_NEW_21 |  | V | varchar | 30 | 30 | DRC! F34 | Ver_NEW_25 | Ver_Gap20 |  |  | varchar | 1
[6 empty] | Ver_POR_22 |  | V | varchar | 25 | Por_20 |  | varchar(5) | V | 25 | POR_27 | Ver_POR_25 |  | Ver_NEW_22 |  | V | varchar | 30 | 20 | Man_06 | Ver_NEW_26 | Ver_Gap21 |  |  | varchar | 1
[6 empty] | Ver_POR_23 |  | V | varchar | 5 | Por_21 |  | varchar(15) | V | 15 | POR_28 | Ver_POR_26 |  | Ver_NEW_23 |  | V | varchar | 15 | 20 | Man_07 | Ver_NEW_27 | Ver_Gap22 |  |  | varchar | 1
[6 empty] | Ver_POR_24 |  | V | varchar | 5 | Por_22 |  | varchar(10) | V | 10 | POR_34 | Ver_POR_27 |  | Ver_NEW_24 |  | V | varchar | 30 | 20 | Man_08 | Ver_NEW_28 | Ver_Gap23 |  |  | varchar | 1
[6 empty] | Ver_POR_25 |  | V | varchar | 25 | Por_23 |  | varchar(1) | V | 10 | POR_50 | Ver_POR_28 |  | Ver_NEW_25 |  | V | varchar | 30 | 15 | Man_09 | Ver_NEW_29 | Ver_Gap24 |  |  | varchar | 1
[6 empty] | Ver_POR_26 |  | V | varchar | 15 | Por_24 |  | varchar(1) | V | 10 | POR_44 | Ver_POR_29 |  | Ver_NEW_26 |  | V | varchar | 20 | 15 | Man_10 | Ver_NEW_30 | Ver_Gap25 |  |  | varchar | 1
[6 empty] | Ver_POR_27 |  | V | varchar | 10 | Por_25 |  | varchar(1) | V | 5 | POR_43 | Ver_POR_30 |  | Ver_NEW_27 |  | V | varchar | 20 | 30 | DIF! D29 | Ver_NEW_31 | Ver_Gap26 |  |  | varchar | 1
[6 empty] | Ver_POR_28 |  | V | varchar | 10 | Por_26 |  | varchar(10) | V | 10 | POR_19 | Ver_POR_31 |  | Ver_NEW_28 |  | V | varchar | 20 | 30 | APP_09 | Ver_NEW_32 | Ver_Gap27 |  |  | varchar | 1
[6 empty] | Ver_POR_29 |  | V | varchar | 10 | Por_27 |  | varchar(25) | V | 5 | POR_35 | Ver_POR_32 |  | Ver_NEW_29 |  | V | varchar | 15 | 30 | APP_11 | Ver_NEW_33 | Ver_Gap28 |  |  | varchar | 1
[6 empty] | Ver_POR_30 |  | V | varchar | 5 | Por_28 |  | varchar(15) | V | 5 | POR_45 | Ver_POR_33 |  | Ver_NEW_30 |  | V | varchar | 15 | 20 | Man_11 | Ver_NEW_34 | Ver_Gap29 |  |  | varchar | 1
[6 empty] | Ver_POR_31 |  | V | varchar | 10 | Por_29 |  | varchar(5) | V | 10 | POR_22 | Ver_POR_34 |  | Ver_NEW_31 |  | V | varchar | 30 | 15 | Man_12 | Ver_NEW_35 | Ver_Gap30 |  |  | varchar | 1
[6 empty] | Ver_POR_32 |  | V | varchar | 5 | Por_30 |  | varchar(15) | V | 5 | 1 | Ver_POR_35 |  | Ver_NEW_32 |  | V | varchar | 30 | 30 | Q&R! E26 | Ver_NEW_36 | Ver_Gap31 |  |  | varchar | 1
[6 empty] | Ver_POR_33 |  | V | varchar | 5 | Por_31 |  | varchar(25) | V | 10 | +/-0.5 | Ver_POR_36 | 0.5 | Ver_NEW_33 |  | V | varchar | 30 | 30 | APP_10 | Ver_NEW_37 | Ver_Gap32 |  |  | varchar | 1
[6 empty] | Ver_POR_34 |  | V | varchar | 10 | Por_32 |  | varchar(25) | V | 10 | +/-10% | Ver_POR_37 | 10 | Ver_NEW_34 |  | V | varchar | 20 | 30 | APP_12 | Ver_NEW_38 | Ver_Gap33 |  |  | varchar | 1
[6 empty] | Ver_POR_35 |  | V | varchar | 5 | Por_33 |  | varchar(20) | V | 10 | +/-10% | Ver_POR_38 | 10 | Ver_NEW_35 |  | V | varchar | 15 | 20 | Man_13 | Ver_NEW_39 | Ver_Gap34 |  |  | varchar | 1
[6 empty] | Ver_POR_36 |  | V | varchar | 10 | Por_34 |  | varchar(10) | V | 10 | <20 um | Ver_POR_39 | 20 | Ver_NEW_36 |  | V | varchar | 30 | 30 | Man_14 | Ver_NEW_40 | Ver_Gap35 |  |  | varchar | 1
[6 empty] | Ver_POR_37 |  | V | varchar | 10 | Por_35 |  | varchar(5) | V | 20 | LF: >2.5 g/mil^2 | Ver_POR_40 | LF: >2.5 g/mil^2 | Ver_NEW_37 |  | V | varchar | 30 | 20 | Man_15 | Ver_NEW_41 | Ver_Gap36 |  |  | varchar | 1
[6 empty] | Ver_POR_38 |  | V | varchar | 10 | Por_36 |  | varchar(5) | V | 10 | <10 % | Ver_POR_41 | 10 | Ver_NEW_38 |  | V | varchar | 30 | 30 | Man_16 | Ver_NEW_42 | Ver_Gap37 |  |  | varchar | 1
[6 empty] | Ver_POR_39 |  | V | varchar | 10 | Por_37 |  | varchar(10) | V | 20 | BGM3A:15~30nm | Ver_POR_42 | BGM3A:15~30nm | Ver_NEW_39 |  | V | varchar | 20 | 30 | Q&R! D30 | Ver_NEW_43 | Ver_Gap38 |  |  | varchar | 1
[6 empty] | Ver_POR_40 |  | V | varchar | 20 | Por_38 |  | varchar(15) | V | 5 | POR_10 | Ver_POR_43 |  | Ver_NEW_40 |  | V | varchar | 30 | 20 | Man_17 | Ver_NEW_44 | Ver_Gap39 |  |  | varchar | 1
[6 empty] | Ver_POR_41 |  | V | varchar | 10 | Por_39 |  | varchar(15) | V | 15 | 58~25747 ea | Ver_POR_44 | 58~25747 | Ver_NEW_41 |  | V | varchar | 20 | 20 | Man_18 | Ver_NEW_45 | Ver_Gap40 |  |  | varchar | 1
[6 empty] | Ver_POR_42 |  | V | varchar | 20 | Por_40 |  | varchar(15) | V | 5 | No | Ver_POR_45 |  | Ver_NEW_42 |  | V | varchar | 30 | 30 | APP_21 | Ver_NEW_46 | Ver_Gap41 |  |  | varchar | 1
[6 empty] | Ver_POR_43 |  | V | varchar | 5 | Por_41 |  | varchar(15) | V | 10 | 22~240 | Ver_POR_46 | 22~240 | Ver_NEW_43 |  | V | varchar | 30 | 30 | APP_11 | Ver_NEW_47 | Ver_Gap42 |  |  | varchar | 1
[6 empty] | Ver_POR_44 |  | V | varchar | 15 | Por_42 |  | varchar(100) | V | 10 | 84~127 | Ver_POR_47 | 84~127 | Ver_NEW_44 |  | V | varchar | 20 | 10 | - | Ver_NEW_48 | Ver_Gap43 |  |  | varchar | 1
[6 empty] | Ver_POR_45 |  | V | varchar | 5 | Por_43 |  | varchar(5) | V | 10 | 10~78 | Ver_POR_48 | 10~78 | Ver_NEW_45 |  | V | varchar | 20 | 10 | - | Ver_NEW_49 | Ver_Gap44 |  |  | varchar | 1
[6 empty] | Ver_POR_46 |  | V | varchar | 10 | Por_44 |  | varchar(10) | V | 10 | 10~29 | Ver_POR_49 | 10~29 | Ver_NEW_46 |  | V | varchar | 30 | 10 | - | Ver_NEW_50 | Ver_Gap45 |  |  | varchar | 1
[6 empty] | Ver_POR_47 |  | V | varchar | 10 | Por_45 |  | varchar(5) | V | 10 | - | Ver_POR_50 |  | Ver_NEW_47 |  | V | varchar | 30 | 20 | Man_19 | Ver_NEW_51 | Ver_Gap46 |  |  | varchar | 1
[6 empty] | Ver_POR_48 |  | V | varchar | 10 | Por_46 |  | varchar(20) | V | 15 | 58~25747 ea | Ver_POR_51 | 58~25747 | Ver_NEW_48 |  | V | varchar | 10 | 30 | DIF! D30 | Ver_NEW_52 | Ver_Gap47 |  |  | varchar | 1
[6 empty] | Ver_POR_49 |  | V | varchar | 10 | Por_47 |  | varchar(10) | V | 15 | 172~18510 | Ver_POR_52 | 172~18510 | Ver_NEW_49 |  | V | varchar | 10 | 30 | APP_09 | Ver_NEW_53 | Ver_Gap48 |  |  | varchar | 1
[6 empty] | Ver_POR_50 |  | V | varchar | 10 | Por_48 |  | varchar(10) | V | 10 | 65~108 | Ver_POR_53 | 65~108 | Ver_NEW_50 |  | V | varchar | 10 | 30 | APP_11 | Ver_NEW_54 | Ver_Gap49 |  |  | varchar | 1
[6 empty] | Ver_POR_51 |  | V | varchar | 15 | Por_49 |  | varchar(10) | V | 10 | 84~138 | Ver_POR_54 | 84~138 | Ver_NEW_51 |  | V | varchar | 20 | 30 | APP_11 | Ver_NEW_55 | Ver_Gap50 |  |  | varchar | 1
[6 empty] | Ver_POR_52 |  | V | varchar | 15 | Por_50 |  | varchar(10) | V | 10 | 30~326 | Ver_POR_55 | 30~326 | Ver_NEW_52 |  | V | varchar | 30 | 30 | APP_11 | Ver_NEW_56 | Ver_Gap51 |  |  | varchar | 1
[6 empty] | Ver_POR_53 |  | V | varchar | 10 | Por_51 |  | varchar(10) | V | 40 | CS/DF: 80~326, CH: 30~326 | Ver_POR_56 | CS/DF: 80~326, CH: 30~326 | Ver_NEW_53 |  | V | varchar | 30 | 30 | APP_11 | Ver_NEW_57 | Ver_Gap52 |  |  | varchar | 1
[6 empty] | Ver_POR_54 |  | V | varchar | 10 | Por_52 |  | varchar(10) | V | 10 | 23~326 | Ver_POR_57 | 23~326 | Ver_NEW_54 |  | V | varchar | 30 | 30 | APP_11 | Ver_NEW_58 | Ver_Gap53 |  |  | varchar | 1
[6 empty] | Ver_POR_55 |  | V | varchar | 10 | Por_53 |  | varchar(10) | V | 20 | 83~140, 200~326 | Ver_POR_58 | 83~140, 200~326 | Ver_NEW_55 |  | V | varchar | 30 | 15 | Man_20 | Ver_NEW_59 | Ver_Gap54 |  |  | varchar | 1
[6 empty] | Ver_POR_56 |  | V | varchar | 40 | Por_54 |  | varchar(10) | V | 10 | POR_48 | Ver_POR_59 |  | Ver_NEW_56 |  | V | varchar | 30 | 15 | Man_21 | Ver_NEW_60 | Ver_Gap55 |  |  | varchar | 1
[6 empty] | Ver_POR_57 |  | V | varchar | 10 | Por_55 |  | varchar(5) | V | 10 | POR_49 | Ver_POR_60 |  | Ver_NEW_57 |  | V | varchar | 30 | 15 | Man_22 | Ver_NEW_61 | Ver_Gap56 |  |  | varchar | 1
[6 empty] | Ver_POR_58 |  | V | varchar | 20 |  |  |  |  | 5 | POR_36 | Ver_POR_61 |  | Ver_NEW_58 |  | V | varchar | 30 | 15 | NA | Ver_NEW_62 | Ver_Gap57 |  |  | varchar | 1
[6 empty] | Ver_POR_59 |  | V | varchar | 10 |  |  |  |  | 15 | POR_38 | Ver_POR_62 |  | Ver_NEW_59 |  | V | varchar | 15 | 15 | NA | Ver_NEW_63 | Ver_Gap58 |  |  | varchar | 1
[6 empty] | Ver_POR_60 |  | V | varchar | 10 |  |  |  |  | 15 | POR_39 | Ver_POR_63 |  | Ver_NEW_60 |  | V | varchar | 15 | 15 | NA | Ver_NEW_64 | Ver_Gap59 |  |  | varchar | 1
[6 empty] | Ver_POR_61 |  | V | varchar | 5 |  |  |  |  | 15 | POR_40 | Ver_POR_64 |  | Ver_NEW_61 |  | V | varchar | 15 | 15 | NA | Ver_NEW_65 | Ver_Gap60 |  |  | varchar | 1
[6 empty] | Ver_POR_62 |  | V | varchar | 15 |  |  |  |  | 15 | POR_41 | Ver_POR_65 |  | Ver_NEW_62 |  | V | varchar | 15 |  |  |  | Ver_Gap61 |  |  | varchar | 1
[6 empty] | Ver_POR_63 |  | V | varchar | 15 | [8 empty] | Ver_NEW_63 |  | V | varchar | 15 |  |  |  | Ver_Gap62 |  |  | varchar | 1
[6 empty] | Ver_POR_64 |  | V | varchar | 15 | [8 empty] | Ver_NEW_64 |  | V | varchar | 15 |  |  |  | Ver_Gap63 |  |  | varchar | 1
[6 empty] | Ver_POR_65 |  | V | varchar | 15 | [8 empty] | Ver_NEW_65 |  | V | varchar | 15 |  |  |  | Ver_Gap64 |  |  | varchar | 1
[27 empty] | Ver_Gap65 |  |  | varchar | 1

## Sheet3
Name | PK | Null | Data Type | Length
Ver_Name | V |  | varchar | 50
Ver_Type | V |  | varchar | 5 | New/Por/Gap
UpdateTime |  |  | Datatime
UserName |  |  | varchar | 10
Ver_Status |  |  | varchar | 1
Ver_Gap1 |  |  | varchar | 50 |  | C_N_V1 | New | qq | wwe | rtt | r
Ver_Gap2 |  |  | varchar | 50 |  | C_N_V1 | Por | jjj | jjjl | lll
Ver_Gap3 |  |  | varchar | 50 |  | C_N_V1 | Y | N | Y | Y
Ver_Gap4 |  |  | varchar | 50
Ver_Gap5 |  |  | varchar | 50
Ver_Gap6 |  |  | varchar | 50
Ver_Gap7 |  |  | varchar | 50
Ver_Gap8 |  |  | varchar | 50
Ver_Gap9 |  |  | varchar | 50
Ver_Gap10 |  |  | varchar | 50
Ver_Gap11 |  |  | varchar | 50
Ver_Gap12 |  |  | varchar | 50
Ver_Gap13 |  |  | varchar | 50
Ver_Gap14 |  |  | varchar | 50
Ver_Gap15 |  |  | varchar | 50
Ver_Gap16 |  |  | varchar | 50
Ver_Gap17 |  |  | varchar | 50
Ver_Gap18 |  |  | varchar | 50
Ver_Gap19 |  |  | varchar | 50
Ver_Gap20 |  |  | varchar | 50
Ver_Gap21 |  |  | varchar | 50
Ver_Gap22 |  |  | varchar | 50
Ver_Gap23 |  |  | varchar | 50
Ver_Gap24 |  |  | varchar | 50
Ver_Gap25 |  |  | varchar | 50
Ver_Gap26 |  |  | varchar | 50
Ver_Gap27 |  |  | varchar | 50
Ver_Gap28 |  |  | varchar | 50
Ver_Gap29 |  |  | varchar | 50
Ver_Gap30 |  |  | varchar | 50
Ver_Gap31 |  |  | varchar | 50
Ver_Gap32 |  |  | varchar | 50
Ver_Gap33 |  |  | varchar | 50
Ver_Gap34 |  |  | varchar | 50
Ver_Gap35 |  |  | varchar | 50
Ver_Gap36 |  |  | varchar | 50
Ver_Gap37 |  |  | varchar | 50
Ver_Gap38 |  |  | varchar | 50
Ver_Gap39 |  |  | varchar | 50
Ver_Gap40 |  |  | varchar | 50
Ver_Gap41 |  |  | varchar | 50
Ver_Gap42 |  |  | varchar | 50
Ver_Gap43 |  |  | varchar | 50
Ver_Gap44 |  |  | varchar | 50
Ver_Gap45 |  |  | varchar | 50
Ver_Gap46 |  |  | varchar | 50
Ver_Gap47 |  |  | varchar | 50
Ver_Gap48 |  |  | varchar | 50
Ver_Gap49 |  |  | varchar | 50
Ver_Gap50 |  |  | varchar | 50
Ver_Gap51 |  |  | varchar | 50
Ver_Gap52 |  |  | varchar | 50
Ver_Gap53 |  |  | varchar | 50
Ver_Gap54 |  |  | varchar | 50
Ver_Gap55 |  |  | varchar | 50
Ver_Gap56 |  |  | varchar | 50
Ver_Gap57 |  |  | varchar | 50
Ver_Gap58 |  |  | varchar | 50
Ver_Gap59 |  |  | varchar | 50
Ver_Gap60 |  |  | varchar | 50
Ver_Gap61 |  |  | varchar | 50
Ver_Gap62 |  |  | varchar | 50
Ver_Gap63 |  |  | varchar | 50
Ver_Gap64 |  |  | varchar | 50
Ver_Gap65 |  |  | varchar | 50

## EPTRA_LV Table
npiEPTRA_LV_Main
Name | PK | Null | Data Type | Length
Ver_Name | V |  | varchar | 80
Ver_No | V |  | varchar | 3
CreateTime |  |  | Datatime
UpdateTime |  |  | Datatime
UserName |  |  | varchar | 10 | Y/N
Ver_Status |  |  | varchar | 1 | Y/N
LV_Signoff_Status |  |  | varchar | 3 | NA/REJ/ACC
Ver_POR_Customer |  |  | varchar | 30
Ver_POR_Device |  |  | varchar | 30
Ver_POR_Site |  |  | varchar | 5
Ver_POR_PKG |  |  | varchar | 25
Ver_POR_WT |  |  | varchar | 5
Ver_POR_FAB |  |  | varchar | 10
Ver_POR_PSV |  |  | varchar | 10
Ver_POR_RVSI |  |  | varchar | 1
Ver_New_Customer |  |  | varchar | 30
Ver_New_Device |  |  | varchar | 30